## Reports
Origional New Features | Hours - Planned
Added New Features | Hours - Actual
Hours -Completed
Origional Bugs
Added Bugs
New Features - Total
In Progress
Completed
Bugs - Total
In Progress
Completed

## Resource
|  |  | Today's Date | 2017-06-15
| KYC |  |  |  | WFM
Dates | Estimated | Actual |  | Dates | Estimated | Actual
Start Date |  |  |  | Start Date | 2016-01-11 | 2016-01-11
End Date |  |  |  | End Date | 2016-02-12 | 2016-02-12
Daily Progress | Project - KYC | Rework |  | Daily Progress | Project - WFM | Rework
Hours Complete | 0 | 0 |  | Hours Complete | 0 | 0
% Complete |  | 0% |  | % Complete |  | #REF!
Projected Hours | Projected | Rework |  | Projected Hours | Projected | Rework
Defect, New Feature, Others | 325 |  |  | Defect, New Feature, Others | #REF!
Projected Rework | 65 |  |  | Projected Rework | #REF!
Actual Rework Created |  | 0 |  | Actual Rework Created |  | #REF!
Regression | 0 |  |  | Regression | #REF!
Projected Rework | 0 |  |  | Projected Rework | #REF!
Total Effort - Individual | 390 | 0 |  | Total Effort - Individual | #REF! | #REF!
Total Effort | 390 |  |  | Total Effort | #REF!
Tickets Progress | New Features | Bugs |  | Tickets Progress | New Features | Bugs
Tickets in QA | 0 | 0 |  | Tickets in QA | 0 | 0
Tickets in Dev |  |  |  | Tickets in Dev
Closed | 0 | 0 |  | Closed | 0 | 0
Total Tickets | 0 | 0 |  | Total Tickets | 0 | 0
Hours | QA Remaining | Hours Available |  | Hours | QA Remaining | Hours Available
Estimated vs Actual | 210 | 117 |  | Estimated vs Actual | 0 | 117
Available Hours | -93 |  |  | Available Hours | 117
KYC
Day Ending On: |  | 0:00
Rohit Kumar |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Garima Bedi |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Vamshi Kher |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Devangi Choudhary |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Total |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Remaining Hours Available |  | 486 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 270 | 252 | 234 | 216 | 198 | 180 | 162 | 144 | 126 | 108 | 90 | 72 | 54 | 36 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Factor Scheduled | Burn Down Rate |  | Daily Factor -->
Rohit Kumar | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Garima Bedi | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Vamshi Kher | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Devangi Choudhary | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
WFM
Day Ending On: |  | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12
Rohit Kumar |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vivek Mittal |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Devangi Choudhary |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Total |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Hours Available |  | 318 | 195 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 186 | 171 | 156 | 141 | 126 | 111 | 96 | 84 | 72 | 60 | 48 | 36 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Factor Scheduled | Burn Down Rate | 2016-01-12: Daily Factor -->
Rohit Kumar | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Vivek Mittal | 6 | bar: 2016-01-11 to 2016-02-12
Devangi Choudhary | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Scheduled Time Off
Holidays/Vacation/Sick | bar: 2016-01-11 to 2016-01-18
Holidays
Rohit Kumar
Garima Bedi
Vamshi Kher
Devangi Choudhary
Plan Release

## Tasks_KYC
Original | Status | Fix Ver | Type | JIRA_ID | Req | Test Prep | Dis/Misc | Test Exe | Total | Total |  | Req | Test Prep | Dis/Misc | Test Exe | Added on
Original | Quality Assurance |  | Others | QA Management |  |  | 100 |  | 100 | 0 | 100
Original | Not Started |  | Others | QA Team Sync up |  |  | 25 |  | 25 | 0 | 25
Original | Not Started |  | Others | Miscellaneous |  |  | 50 |  | 50 | 0 | 50
Original | Not Started |  | Others | Call w/Dev |  |  | 15 |  | 15 | 0 | 15
Original | Not Started |  | Others | Call w/Product |  |  | 25 |  | 25 | 0 | 10
Original | Not Started |  | Others | Regression |  |  | 100 |  | 100 | 0 | 100
Original | Not Started |  | Others | Documentation |  |  | 10 |  | 10 | 0 | 10
Original | New |  | Improvement | CPM-26372 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26335 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26329 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26326 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26325 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26324 | [11 empty] | 2017-06-14
Original | New |  | Improvement | CPM-26304 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26284 | [11 empty] | 2017-06-14
Original | Quality Assurance |  | Improvement | CPM-26283 | [11 empty] | 2017-06-14
Original | Requirements |  | Improvement | CPM-26250 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26207 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26205 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26203 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26201 | [11 empty] | 2017-06-14
Original | Open |  | Bug | CPM-26199 | [11 empty] | 2017-06-14
Original | Development |  | Development | CPM-26196 | [11 empty] | 2017-06-14
Original | Requirements |  | Requirements | CPM-26194 | [11 empty] | 2017-06-14
Original | Open |  | Open | CPM-26191 | [11 empty] | 2017-06-14
Original | Open |  | Open | CPM-26189 | [11 empty] | 2017-06-14
Original | Ready for QA |  | Ready for QA | CPM-26188 | [11 empty] | 2017-06-14
Original | Open |  | Open | CPM-26187 | [11 empty] | 2017-06-14
Original | Open |  | Open | CPM-26185 | [11 empty] | 2017-06-14
Original | Open |  | Open | CPM-26182 | [11 empty] | 2017-06-14
Original | Open |  | Open | CPM-26176 | [11 empty] | 2017-06-14

## Daily_KYC
|  |  | Rohit |  |  |  | Garima |  |  |  | Vamshi |  |  |  | Devangi |  |  |  | Pratyush
Date | Task/JIRA | Status | Req | Design | Exec | Dis/Misc | Req | Design | Exec | Dis/Misc | Req | Design | Exec | Dis/Misc | Req | Design | Exec | Dis/Misc | Req | Design | Exec | Dis/Misc
2016-04-01 | 50001 | Closed | 1 | 12
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06
2015-03-06

## JIRA_Export KYC
Key | Summary | Status | Updated | Issue Type | Reporter | Created | Assignee | Priority-ECTRG | QA Fix Version | Resolved | Component/s | Priority | Priority- | Priority | Fix Version/s
CPM-26372 | GS Template email template changes | New | 2017-06-14 14:48 | Improvement | Michael Celi | 2017-06-14 14:47 | Vitalii Barash | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26335 | Mandatory columns are not present in Available columns section in Add/Delete Columns Page at Sender and Receiver side | Open | 2017-06-13 17:48 | Bug | Ritesh Shende | 2017-06-13 16:40 | Vitalii Barash | Non urgent |  |  |  | Low |  |  | O360: 2.2
CPM-26329 | On disclosure, you can't un-link when initially setting to NA | Open | 2017-06-13 15:28 | Bug | Abdus Aziz | 2017-06-13 15:28 | Ashish Gupta | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26326 | Highlight in red required fields that were not entered on the RFI | Open | 2017-06-13 15:14 | Bug | Abdus Aziz | 2017-06-13 15:14 | Ashish Gupta | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26325 | Special characters entered on guidance/clarification request freezes the pop-up when clicking submit | Open | 2017-06-13 15:12 | Bug | Abdus Aziz | 2017-06-13 15:12 | Ashish Gupta | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26324 | Campaign Outreach Response Report boolean values should show as Yes/No | Open | 2017-06-13 15:08 | Bug | Abdus Aziz | 2017-06-13 15:08 | Sudheer Senisetty | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26304 | Tying Email Template to Campaigns | New | 2017-06-13 17:55 | Improvement | Abdus Aziz | 2017-06-12 20:53 | Abdus Aziz | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26284 | PDF Doiwnload¦ Clicking on PDF Download button showing an error - page not available | Open | 2017-06-13 19:52 | Bug | Shivangi Saroha | 2017-06-10 10:04 | Michael Celi | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26283 | Updates to Preferred Entity Lists | Quality Assurance | 2017-06-14 10:34 | Improvement | Lauren Lim | 2017-06-09 22:40 | Kapil Rawat | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26250 | Guidance and Clarification flow - changes | Requirements | 2017-06-09 21:30 | Improvement | Michael Celi | 2017-06-07 21:25 | Irina Slobodinsky | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26207 | Sorting is incorrect for Uploaded Date column on Add Document modal window | Open | 2017-06-06 15:13 | Bug | Garima Bedi | 2017-06-06 14:42 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26205 | Document is displayed as linked to content even when content has been deleted | Open | 2017-06-06 15:16 | Bug | Garima Bedi | 2017-06-06 14:22 | Irina Slobodinsky | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26203 | Unable to search for documents since Search Box is missing from Add Document modal window | Open | 2017-06-06 15:12 | Bug | Garima Bedi | 2017-06-06 14:13 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26201 | Count mismatch when user click on any value in 'JURISDICTION' and 'ACTIVE TIMELINE' at receiver side | Open | 2017-06-06 15:19 | Bug | Ritesh Shende | 2017-06-06 13:43 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26199 | Receiver Dashboard ¦ LEI Request is still displayed under Selected Content and Total Content count, when it is marked as 'No Outreach Required' | Open | 2017-06-06 15:09 | Bug | Garima Bedi | 2017-06-06 13:17 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26196 | Content name is wrapped too much on content details page on Sender dashboard | Development | 2017-06-08 02:09 | Bug | Garima Bedi | 2017-06-06 10:43 | Nazar Ilkiv | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26194 | Change capture position and receiver display of various items at content level | Requirements | 2017-06-13 23:57 | Improvement | Lauren Lim | 2017-06-05 20:51 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26191 | Entity does not appear in the Counter party entity list on Entity Selection Tab | Open | 2017-06-06 15:18 | Bug | Rohit K | 2017-06-05 17:00 | Irina Slobodinsky | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26189 | Glief Data is getting populated when user clicks on Legal name twice or thrice on Standard LEI Request & Standard Plus- LEI Request + custom RFI questions | Open | 2017-06-13 22:00 | Bug | Shivangi Saroha | 2017-06-05 16:29 | Irina Slobodinsky | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26188 | Count mismatch when user click on any bar in 'ACTIVE CAMPAIGN RESPONSE STATUS' | Ready for QA | 2017-06-08 10:55 | Bug | Kapil Rawat | 2017-06-05 16:18 | Jing Luo | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26187 | Sender dashboard ¦ Guidance/Clarification is displayed as Responded instead of Withdrawn in the downloaded PDF | Open | 2017-06-05 16:57 | Bug | Garima Bedi | 2017-06-05 16:15 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26185 | Sender able to respond to a clarification when the status of the content is 'Responded - Re-Submitted' | Open | 2017-06-05 22:28 | Bug | Kapil Rawat | 2017-06-05 15:41 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26182 | Edit button should not be displayed on Content Details page | Open | 2017-06-05 15:15 | Bug | Garima Bedi | 2017-06-05 14:35 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26176 | Question Library ¦ "Linked Content'' column upward sorting arrow is not showing correct result | Open | 2017-06-05 15:10 | Bug | Gunjan Sachdeva | 2017-06-05 12:23 | Irina Slobodinsky | Non urgent |  |  |  | Medium |  |  | O360: 2.2
O360: 2.2
O360: 2.2
O360: 2.2
O360: 2.2
O360: 2.2
O360: 2.2
O360: 2.2
O360: 2.2