## JIRA_Export_KYC
Key | Summary | Status | Updated | Issue Type | Reporter | Created | Assignee | Priority-ECTRG | QA Fix Version | Resolved | Component/s | Priority | Priority- | Priority | Fix Version/s
CPM-26372 | GS Template email template changes | New | 2017-06-14 14:48 | Improvement | Michael Celi | 2017-06-14 14:47 | Vitalii Barash | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26335 | Mandatory columns are not present in Available columns section in Add/Delete Columns Page at Sender and Receiver side | Open | 2017-06-13 17:48 | Bug | Ritesh Shende | 2017-06-13 16:40 | Vitalii Barash | Non urgent |  |  |  | Low |  |  | O360: 2.2
CPM-26329 | On disclosure, you can't un-link when initially setting to NA | Open | 2017-06-13 15:28 | Bug | Abdus Aziz | 2017-06-13 15:28 | Ashish Gupta | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26326 | Highlight in red required fields that were not entered on the RFI | Open | 2017-06-13 15:14 | Bug | Abdus Aziz | 2017-06-13 15:14 | Ashish Gupta | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26325 | Special characters entered on guidance/clarification request freezes the pop-up when clicking submit | Open | 2017-06-13 15:12 | Bug | Abdus Aziz | 2017-06-13 15:12 | Ashish Gupta | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26324 | Campaign Outreach Response Report boolean values should show as Yes/No | Open | 2017-06-13 15:08 | Bug | Abdus Aziz | 2017-06-13 15:08 | Sudheer Senisetty | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26304 | Tying Email Template to Campaigns | New | 2017-06-13 17:55 | Improvement | Abdus Aziz | 2017-06-12 20:53 | Abdus Aziz | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26284 | PDF Doiwnload¦ Clicking on PDF Download button showing an error - page not available | Open | 2017-06-13 19:52 | Bug | Shivangi Saroha | 2017-06-10 10:04 | Michael Celi | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26283 | Updates to Preferred Entity Lists | Quality Assurance | 2017-06-14 10:34 | Improvement | Lauren Lim | 2017-06-09 22:40 | Kapil Rawat | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26250 | Guidance and Clarification flow - changes | Requirements | 2017-06-09 21:30 | Improvement | Michael Celi | 2017-06-07 21:25 | Irina Slobodinsky | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26207 | Sorting is incorrect for Uploaded Date column on Add Document modal window | Open | 2017-06-06 15:13 | Bug | Garima Bedi | 2017-06-06 14:42 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26205 | Document is displayed as linked to content even when content has been deleted | Open | 2017-06-06 15:16 | Bug | Garima Bedi | 2017-06-06 14:22 | Irina Slobodinsky | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26203 | Unable to search for documents since Search Box is missing from Add Document modal window | Open | 2017-06-06 15:12 | Bug | Garima Bedi | 2017-06-06 14:13 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26201 | Count mismatch when user click on any value in 'JURISDICTION' and 'ACTIVE TIMELINE' at receiver side | Open | 2017-06-06 15:19 | Bug | Ritesh Shende | 2017-06-06 13:43 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26199 | Receiver Dashboard ¦ LEI Request is still displayed under Selected Content and Total Content count, when it is marked as 'No Outreach Required' | Open | 2017-06-06 15:09 | Bug | Garima Bedi | 2017-06-06 13:17 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26196 | Content name is wrapped too much on content details page on Sender dashboard | Development | 2017-06-08 02:09 | Bug | Garima Bedi | 2017-06-06 10:43 | Nazar Ilkiv | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26194 | Change capture position and receiver display of various items at content level | Requirements | 2017-06-13 23:57 | Improvement | Lauren Lim | 2017-06-05 20:51 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26191 | Entity does not appear in the Counter party entity list on Entity Selection Tab | Open | 2017-06-06 15:18 | Bug | Rohit K | 2017-06-05 17:00 | Irina Slobodinsky | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26189 | Glief Data is getting populated when user clicks on Legal name twice or thrice on Standard LEI Request & Standard Plus- LEI Request + custom RFI questions | Open | 2017-06-13 22:00 | Bug | Shivangi Saroha | 2017-06-05 16:29 | Irina Slobodinsky | Non urgent |  |  |  | High |  |  | O360: 2.2
CPM-26188 | Count mismatch when user click on any bar in 'ACTIVE CAMPAIGN RESPONSE STATUS' | Ready for QA | 2017-06-08 10:55 | Bug | Kapil Rawat | 2017-06-05 16:18 | Jing Luo | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26187 | Sender dashboard ¦ Guidance/Clarification is displayed as Responded instead of Withdrawn in the downloaded PDF | Open | 2017-06-05 16:57 | Bug | Garima Bedi | 2017-06-05 16:15 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26185 | Sender able to respond to a clarification when the status of the content is 'Responded - Re-Submitted' | Open | 2017-06-05 22:28 | Bug | Kapil Rawat | 2017-06-05 15:41 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26182 | Edit button should not be displayed on Content Details page | Open | 2017-06-05 15:15 | Bug | Garima Bedi | 2017-06-05 14:35 | Vitalii Barash | Non urgent |  |  |  | Medium |  |  | O360: 2.2
CPM-26176 | Question Library ¦ "Linked Content'' column upward sorting arrow is not showing correct result | Open | 2017-06-05 15:10 | Bug | Gunjan Sachdeva | 2017-06-05 12:23 | Irina Slobodinsky | Non urgent |  |  |  | Medium |  |  | O360: 2.2